## WorkloadSummary
Name | First Task |  | Second Task |  | Third Task |  | Forth Task |  | Fifth Task
| Task Name | Finish Date | Task Name | Finish Date | Task Name | Finish Date | Task Name | Finish Date | Task Name | Finish Date
Beatrix | Project Alpha - Analysis | 2026-04-17
Herindra
Care BA
Azdan
Laili
Cici
Yosy
| Beatrix | Herindra | Rifqi | Azdan | Laili | Cici | Yosy
Stakeholder Interviews | 1 | 0 | 0 | 0 | 0 | 0 | 0
Requirements Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI/UX Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
System Architecture Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test Case Creation | 0 | 0 | 0 | 0 | 0 | 0 | 0
Frontend & Backend Development | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Acceptance Test | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deployment to Production | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post-Deployment Support | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed | 6 | 4 | 0 | 7 | 2 | 0 | 0
Idle | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workload % | 25% | 0% | 0% | 0% | 0% | 0% | 0%
Utilization Cost Plan | 3.958%
Utilization Cost Actual

## ResourceAllocation
ActivityName | Resource | Category | Phase | TaskName | Plan |  |  |  | Actual |  | Workload | Remarks
[5 empty] | TaskStart | TaskEnd | Cost Project | Cost monthly | TaskStart | TaskEnd
Project Alpha - Analysis | Beatrix | Medium | Requirement Gathering & Analysis | Stakeholder Interviews | 2026-01-07 | 2026-04-17 | 118750 | 39583.3333 | 2026-01-07 | 2025-05-12 | 25%
Penyesuaian Parameter Smartdrive TOC : 0224, 0209, 0226, 0227 | Herindra | Medium | Completed | Completed | 2025-02-18 | 2025-06-13 | 296875 | 98958.3333 | 2025-02-18 |  | 0%
Data Anonymization CGISS & CHISS | Herindra | Medium | Completed | Completed | 2025-02-17 | 2025-06-12 | 296875 | 98958.3333 | 2025-02-17 |  | 0%
BCAF Automation | Herindra | Medium | Completed | Completed | 2025-02-01 | 2025-05-23 | 296875 | 98958.3333 | 2025-02-01 |  | 0%
Enhancement Uploader Mypage data qyc (UP15, UP75, UP286, UP289, UP279) | Herindra | Medium | Completed | Completed | 2025-03-01 | 2025-06-23 | 296875 | 98958.3333 | 2025-03-01 |  | 0%
Auto settlement | Azdan | Low | Completed | Completed | 2025-03-01 | 2025-04-11 | 190312.5 | 190312.5 | 2025-03-01 |  | 0%
Revamp & New Scheme in Retail Biz | Azdan | Medium | Completed | Completed |  | 1900-04-10 | 249375 | 83125 | 0 |  | 0%
Bilingual Document | Azdan | Medium | Completed | Completed |  | 1900-04-10 | 249375 | 83125 | 0 |  | 0%
SNAP BI H2H | Azdan | Medium | Completed | Completed |  | 1900-04-10 | 249375 | 83125 | 0 |  | 0%
SNAP BI VA | Azdan | Medium | Completed | Completed |  | 1900-04-10 | 249375 | 83125 | 0 |  | 0%
Merimen – Output Certificate Bilingual Version | Azdan | Low | Completed | Completed |  | 1900-02-06 | 190312.5 | 190312.5 | 0 |  | 0%
CHISS 2nd phase | Beatrix | High | Completed | Completed | 2026-01-07 | 2026-05-29 | 187500 | 46875 | 2026-01-07 |  | 0%
Fasttrack | Beatrix | Medium | Completed | Completed | 2026-01-07 | 2026-04-17 | 118750 | 39583.3333 | 2026-01-07 |  | 0%
Date of Payment | Beatrix | Low | Completed | Completed | 2026-01-07 | 2026-02-13 | 90625 | 90625 | 2026-01-07 |  | 0%
Promedicare | Beatrix | Medium | Completed | Completed | 2026-01-07 | 2026-04-17 | 118750 | 39583.3333 | 2026-01-07 |  | 0%
Update Engine CHISS | Beatrix | Low | Completed | Completed | 2025-04-19 | 2025-05-27 | 90625 | 90625 | 2025-04-19 | 2025-06-22 | 0%
Smartmedicare | Beatrix | Medium | Completed | Completed | 2025-08-25 | 2025-12-04 | 118750 | 39583.3333 | 2025-08-25 |  | 0%
RRTS | Laili | Medium | Completed | Completed |  | 1900-04-10 | 225625 | 75208.3333 | 0 |  | 0%
Update Engine | Laili | Low | User Acceptation Test | Completed |  | 1900-02-06 | 172187.5 | 172187.5 | 0 |  | 0%
New CLP (Ciputra) | Azdan | High | Completed | Completed | 2025-07-01 | 2025-09-30 | 393750 | 196875 | 2025-07-01 | 2025-09-30 | 0%
Formulas:
TaskEnd = IFNA(WORKDAY([Plan],XLOOKUP([Category],Library!$V3:V5,Library!$W3:W5),VSTACK(ImportantDate!B3:B23,IFERROR(_xlws.FILTER(ImportantDate!$F3:F100,ImportantDate!$E3:E100=ResourceAllocation!B3),"1-Jan-2025"))),"")
Cost monthly = [Cost Project]/DATEDIF([Plan],[TaskEnd],"m")
Actual = [Plan]

## ImportantDate
Indonesia Public Holiday |  | Leave Plan
|  | Name | Dates | 2025-01-01 | 244
2025-01-01 | New Year's Day | Beatrix | 2025-03-20 | 2025-12-31
2025-01-27 | Isra Mi'raj | ResourceName1
2025-01-29 | Chinese New Year
2025-03-29 | Bali Hindu New Year (Silence Day)
2025-03-31 | Eid al-Fitr
2025-04-01 | Eid al-Fitr
2025-04-02 | Mass Leave Eid al-Fitr
2025-04-03 | Mass Leave Eid al-Fitr
2025-04-04 | Mass Leave Eid al-Fitr
2025-04-07 | Mass Leave Eid al-Fitr
2025-04-18 | Good Friday
2025-04-20 | Easter Sunday
2025-05-01 | Labour Day
2025-05-12 | Waisak Day
2025-05-29 | Ascension Day of Jesus Christ
2025-06-01 | Pancasila Day
2025-06-06 | Eid al-Adha
2025-06-27 | Islamic New Year
2025-08-17 | Independence Day
2025-09-05 | Prophet Muhammad's Birthday
2025-12-25 | Christmas Day

## Library
[9 empty] | Low |  |  | Medium |  |  | High
ResourceID | ResourceName | Type | Max Hours / Week |  | No | Phase | Task ID | Task Name | Duration (Days) | Duration (Hours) | Percentage | Duration (Days) | Duration (Hours) | Percentage | Duration (Days) | Duration (Hours) | Percentage |  | Days | BA | PM | Dev
R1 | Beatrix | BA | 40 |  | 1 | Requirement Gathering & Analysis | T001 | Stakeholder Interviews | 2 | 1 | 12.5% | 5 | 2 | 25% | 10 | 4 | 50% | Low | 27 | 14.5
R2 | Herindra | BA | 40 |  |  | Requirement Gathering & Analysis | T002 | Requirements Documentation | 2 | 2 | 25% | 5 | 3 | 37.5% | 10 | 4 | 50% | medium | 72 | 19
R3 | Care BA | BA | 40 |  | 2 | Design | T003 | UI/UX Design | 3 | 1 | 12.5% | 7 | 2 | 25% | 7 | 3 | 37.5% | High | 102 | 30
R4 | Azdan | BA | 40 |  |  | Design | T004 | System Functional Design | 1 | 1 | 12.5% | 5 | 1 | 12.5% | 7 | 2 | 25%
R5 | Laili | BA | 40 |  | 3 | Implementation | T005 | Test Case Creation | 2 | 2 | 25% | 3 | 2 | 25% | 5 | 4 | 50%
R6 | Cici | PM | 40 |  |  | Implementation | T006 | Frontend & Backend Development | 10 | 1 | 12.5% | 20 | 1 | 12.5% | 30 | 4 | 50%
R7 | Yosy | PM | 40 |  | 4 | Testing | T007 | Integration Testing | 2 | 2 | 25% | 5 | 2 | 25% | 8 | 3 | 37.5%
[7 empty] | T008 | User Acceptance Test | 2 | 3 | 37.5% | 5 | 3 | 37.5% | 8 | 3 | 37.5%
[5 empty] | 5 | Deployment | T009 | Deployment to Production | 2 | 1 | 12.5% | 2 | 2 | 25% | 2 | 2 | 25%
[5 empty] | 6 | Maintenance |  | Post-Deployment Support | 1 | 0.5 | 6.25% | 15 | 1 | 12.5% | 15 | 1 | 12.5%
[5 empty] | 7 | Idle |  | Idle | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
[5 empty] | 8 | Completed |  | Completed | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
[8 empty] | Estimation Effort | 27 | 14.5 |  | 72 | 19 |  | 102 | 30
[8 empty] | 1 cycle of activity | 2.4469 |  |  | 8.55 |  |  | 19.125
Resource Cost | Cost |  | Per day cost | Per hour cost
CARE BA | 2000000 |  | 100000 | 12500
Herindra | 2500000 |  | 125000 | 15625
Beatrix | 1000000 |  | 50000 | 6250
Azdan | 2100000 |  | 105000 | 13125
Laili | 1900000 |  | 95000 | 11875